## Sheet1
Module | Sub Module | Allocated to | Start Date | End Date | Actual Start Date | Actual End Date | Comments | Status | Allocated Days | Actual Days Taken
29-Oct-2017 to 18-Nov-2017
My Relationship |  | Nikhitha | 2017-11-15 | 2017-11-16 | 2017-11-15 | 2017-11-16 |  | Completed | 1.5 | 2
Loan Simulation |  | Nikhitha | 2017-11-08 | 2017-11-16 | 2017-11-08 | 2017-11-22 |  | Completed | 1.5 | 2
Deposit Simulation |  | Nikhitha | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 |  | Completed | 1 | 1
Pre-login |  | Gowtham | 2017-11-03 | 2017-11-14 | 2017-11-03 | 2017-11-14 |  | Completed | 8
Login |  | Gowtham | 2017-11-13 | 2017-11-13 | 2017-11-13 | 2017-11-13 |  | Completed | 1
Dashboard |  | Gowtham | 2017-11-15 | 2017-11-17 | 2017-11-15 | 2017-11-20 |  | Completed | 3 | 4
My Tasks |  | Nikhitha | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 |  | Completed | 0.5 | 1
Accounts | Details | Nikhitha | 2017-11-17 | 2017-11-17 | 2017-11-17 | 2017-11-17 |  | Completed | 0.5 | 1
| Transactions | Nikhitha | 2017-11-17 | 2017-11-17 | 2017-11-21 | 2017-11-21 |  | Completed | 0.5 | 1
17.5
19-Nov-2017 to 25-Nov-2017
Admin Module Discussion |  | Gowtham | 2017-11-20 | 2017-11-20 | 2017-11-20 | 2017-11-20 |  | Completed | 0.5
Base app creation and micro app integration |  | Gowtham | 2017-11-21 | 2017-11-21 | 2017-11-21 | 2017-11-21 |  | Completed | 0.5
Drag node chart R&D |  | Gowtham | 2017-11-21 | 2017-11-21 | 2017-11-21 | 2017-11-21 |  | Completed | 0.5
Loans | Details | Nikhitha | 2017-11-21 | 2017-11-21 | 2017-11-21 | 2017-11-21 |  | Completed | 0.5 | 0.5
| Transactions | Nikhitha | 2017-11-22 | 2017-11-22 | 2017-11-22 | 2017-11-22 |  | Completed | 0.5 | 0.5
Deposits | Details | Nikhitha | 2017-11-21 | 2017-11-21 | 2017-11-21 | 2017-11-21 |  | Completed | 0.5 | 0.5
Hierarchy Chart |  | Gowtham | 2017-11-22 | 2017-11-22 | 2017-11-22 | 2017-11-22 |  | Completed | 1
Navigator App |  | Gowtham | 2017-11-23 | 2017-11-23 | 2017-11-23 | 2017-11-23 | List inside list has alignment issues.IDE to fix the issue | Completed | 0.5
Sidebar for MicrApps |  | Nikhitha | 2017-11-23 | 2017-11-23 | 2017-11-23 | 2017-11-23 |  | Completed | 0.5 | 0.5
Standardiztion of fonts and alignment according to 3.2 Corporate app |  | Nikhitha | 2017-11-24 | 2017-11-24 | 2017-11-24 |  |  | Completed | 1 | 1
6
26-Nov-2017 to 02-Dec-2017
Transfers | Own A/c,within bank,others domestic,other international,manage beneficiary | Nikhitha | 2017-11-27 | 2017-11-27 | 2017-11-27 |  | Own A/c,withinbank completed except progessive step. Other bank domestic and international i have done screen and few functionality. I will finish this screen once am back. | WIP | 1
Trade Finance | LC | Gowtham | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-28 |  | Completed | 1 | 2
Payments |  | Ashwath | 2017-11-27 | 2017-11-28 | 2017-11-27 |  |  |  | 2
Admin | Corporate profile,entity profile | Gowtham | 2017-11-29 | 2017-11-29 | 2017-11-29 | 2017-11-29 |  | Completed | 1 | 1
| Role Mapping | Gowtham | 2017-11-30 | 2017-12-01 | 2017-11-30 | 2017-12-04 |  | Completed | 2 | 3
Email : apzcorporate@gmail.com
Password : i-exceed001

## Sheet2
WIP
Completed
Not Started